## Sheet1
Claire Petras
ENGL 4740 UC Denver English Honors in Writing
Professor Rodney Herring
Spring 2013 |  | 1/22-1/27 | 1/28-2/3 | 2/4-2/10 | 2/11-2/17 | 2/18-2/24 | 2/25-3/3 | 3/4-3/10 | 3/11-3/17 | 3/18-3/24 | 3/25-3/31 | 4/1-4/7 | 4/8-4/14 | 4/15-4/21 | 4/22-4/28 | 4/29-5/5 | 5/6-5/12 | 5/13-5/18
[11 empty] | Spring | [6 empty] | Graduation!
Timeline |  | wk 1 | wk 2 | wk 3 | wk 4 | wk 5 | wk 6 | wk 7 | wk 8 | wk 9 | Break | wk 10 | wk 11 | wk 12 | wk 13 | wk 14 | wk 15 | wk 16
Deliverables | Design document | bar: wk 3
Project Plan | bar: wk 3
| Design a style guide | [9 empty] | ✓
Timeline | bar: wk 5
Storyboarding | bar: wk 5
| Sitemap | [11 empty] | ✓
| Wireframes | wk 6: here
| Flowcharts | wk 6: here
| Content Inventory | [9 empty] | ✓ | ✓ | ✓ | ✓ | ✓ | bar: wk 4 to wk 9
| Blog | [9 empty] | ✓ | ✓ | ✓ | ✓ | ✓ | bar: wk 1 to wk 9
| Usability testing | [11 empty] | ✓ | ✓
| Second reader-Nicole | [13 empty] | here
| Submission-Rodney, Committee | [14 empty] | HERE!!
| Oral Defence | [14 empty] | HERE!!
2013-04-29 12:30
Design | conceptualize-how do I want to tell this story? | bar: wk 5
page layout - post its | bar: wk 5
| define site colors, fonts, layout-style guide and CSS | [9 empty] | ✓
storyboard the site by hand, scan | bar: wk 5
define navigation for site-sitemap | bar: wk 6
| determine layout grids for home, main pages-wireframe | [11 empty] | ✓
| document processes within site-flowcharts | wk 6: here
Build | home page-program layout, position, fonts, background, CSS | bar: wk 7 to wk 9
| primary global nav, secondary global nav, submenus | [9 empty] | ✓ | bar: wk 9
| content for all pages, graphics, animation, multimedia | [10 empty] | ✓ | ✓
| draft up usability testing requirements (see project plan) | [11 empty] | ✓
| implement usability testing | [12 empty] | ✓ | ✓
| editing, fixing, extras | [12 empty] | ✓ | ✓
| draft up usability testing findings | [13 empty] | here
weekly | ready to go, paperwork, set up blog | bar: wk 1
completes | Dreamweaver, design ideas | bar: wk 2
reading-wireframes, project planning | bar: wk 3
project mgmt-doc design, project plan, timeline, content inventory | bar: wk 4
conceptualize-layout, storyboards | bar: wk 5
begin programming in Dreamweaver | bar: wk 7